## Sheet1
Story ID | Story Name | Description | Priority | Iteration (Sprint) number | Acceptance Criteria | Estimation | Notes | Date started (or planned) | Date finished (or planned)
PB-001 | TA - Register Account & Complete CV | As a TA, I need to register an account and complete my resume to apply for TA positions. | High | Sprint 1 | 1. Support email/student ID registration with mandatory field checks; 2. Allow PDF/text resume upload (education/skills/experience); 3. Require email verification post-registration
PB-002 | TA - View Available TA Positions | As a TA, I need to view available TA positions to filter target roles. | High | Sprint 1 | 1. Show course name, TA quota, deadline, skill requirements; 2. Support filtering by course/deadline; 3. Allow clicking to view position details
PB-003 | MO - Publish TA Position Needs | As a MO, I need to publish TA position needs to recruit qualified TAs. | High | Sprint 1 | 1. Require filling course name, TA count, duties, skills, deadline; 2. Allow preview/editing before publishing; 3. Sync published positions to the list automatically
PB-004 | MO - Review TA Applications | As a MO, I need to review TA applications for my course to select candidates. | Medium | Sprint 2 | 1. Display applicant name, resume link, application time; 2. Support filtering by skills/education; 3. Allow "Pass/Fail" marking with comments
PB-005 | Admin - Approve MO's Positions | As an Admin, I need to approve MO-published positions to ensure compliance. | Low | Sprint 2 | 1. Highlight pending positions in red; 2. Support "Approve/Reject" (rejection needs reason); 3. Make positions visible to TAs only after approval
PB-006 | TA - Submit Position Application | As a TA, I need to submit position applications to participate in TA selection. | High | Sprint 1 | 1. Require confirming resume info before submission; 2. Allow adding additional notes; 3. Show "submission success" prompt post-application
PB-007 | TA - Check Application Status | As a TA, I need to check my application status to track selection progress. | Medium | Sprint 2 | 1. Show "Pending/Passed/Failed" status for each application; 2. Display MO's feedback if failed; 3. Send notifications for status updates
PB-008 | MO - Generate TA Offer Letters | As a MO, I need to generate TA offer letters to inform candidates of results. | Medium | Sprint 3 | 1. Support selecting passed TAs to auto-generate offer templates; 2. Allow editing offer content (position info, onboarding time); 3. Support emailing offers
PB-009 | Admin - View Recruitment Statistics | As an Admin, I need to view recruitment stats to track overall progress. | Low | Sprint 3 | 1. Show application count, hire count, and unfilled positions per course; 2. Support exporting stats reports by time period; 3. Update data in real time
PB-010 | All Roles - Reset Account Password | As a user, I need to reset my password to regain access if I forget it. | Medium | Sprint 3 | 1. Support password reset via registered email (verification code); 2. Require new password to meet complexity (8+ chars, letter+number); 3. Force re-login after reset